## Sheet1
Activity ID | Activity | Assigned Team | 2017-03-04 | 2017-03-05 | 2017-03-10 | 2017-03-11 | 2017-03-12 | 2017-03-14 | 2017-03-16 | 2017-03-17 | 2017-03-18 | 2017-03-19 | 2017-03-25 | 2017-03-27 | 2017-04-01 | 2017-04-05 | 2017-04-10 | 2017-04-15 | 2017-04-24 | 2017-04-26 | 2017-04-28 | 2017-04-30 | 5/3 | 5/6 | 2017-05-08 | 2017-05-10
A | Submit preferred team in an online form | All members
B | Choose teams according to preferences | Leader - Co-leader
C | Discussing and finalizing signed agreement with other teams | Leader - Co-leader
D | Research problem, past projects and tools | Research and Design Team
E | Research machine learning solutions | Research and Design Team
F | General team meeting | All members
G | Internal I/O interface design | Research and Design Team
H | Communication interface design | Research and Design Team
I | Implementation logic design | Research and Design Team
J | Implementation logic version controlled code | Implementation Team
K | Fixing bugs and generating bug report | Implementation Team
L | Communication code commited to Github | Integration & Communication & Testing Team
M | Layers of abstraction between integration and both implementation and integration | Integration & Communication & Testing Team
N | Integration code committed to Github | Integration & Communication & Testing Team
O | Bug-reports issued to implementation team | Integration & Communication & Testing Team
P | GUI design and tools that will be used | Interface & Documentation Team
Q | Working GUI | Interface & Documentation Team
R | Generate test cases scenarios | Integration & Communication & Testing Team
S | Document research and design team's work | Interface & Documentation Team
T | Document implementation, integration and interface teams' work | Interface & Documentation Team
Color Code
| Team | Color Id
All members
Leader - Co-leader
Research and Design Team
Implementation Team
Integration & Communication & Testing Team
Interface & Documentation Team